## Slide 1: Update Steering Committee
11-12-2020

## Slide 2: Status update – SEM Pilot: Proof of Concept Project lead: Marcel Untied Date: December 11th 2020
DELIVERABLES | Deadline | Status in % | Remark
Start Project team | 7-12-2020 |  | 
Develop API’s | 31-1-2021 |  | Iddink will start in January and expects to be ready mid/end February (2/3 sprints)
Functional: - Test scenarios | 15-1-2021 |  | 
Technical: Adjusted API designs Design additional API’s (Usage, results & Progress) Design functionality | 15-1-2021 |  | Update 18 December in project team meeting
Design Mock-up frontend | 31-1-2021 |  | 
Link API’s in acceptance environment | 28-2-2021 |  | Depends on API development
Ongoing as planned/targeted
Ongoing, some challenges
Ongoing, significant challenges
Not started/applicable
Summary update
Highlights and key learnings
# | Description Risk | Impact |  | Mitigation | Due date | Owner | Status
1 | Execution POC phase (February) not according to (concept) planning | Medium |  | Move execution to march and evaluation to April (possible risk resources PSS) | 15-1-2021 | Marchien | Planned
2 | POC will not deliver the desired information to make decisions on next steps | High |  | Make clear how results are shared during demo’s and board meetings and share approach with stake holders (mock-up) frontend | 31-1-2021 | Marchien/Marcel | Planned
Decisions needed from Steerco
Completed activities
Planned activities
*
Project team started
Development API’s started
Iddink will start developing in January (2nd half)
Participation Thieme still unclear
Scope of the demo: Work with (mock-up) frontend to show how ecosystem works
First Project Team meeting
  Notes 4 December
Actions (deliverables) assigned to project team members
Pilot team meetings planned till end of February (every two weeks)
Determine testscenario’s
Adjusted API designs (Entitlement, Catalogue)
Design Setup functionality
Design Results & Progress API
Design Usage API
No decisions needed, but planning has to be discussed